## DETALLES DEL PROYECTO
ID PROYECTO
NOMBRE PROYECTO
PROJECT MANAGER
FECHA
VERSION

## SPRINT 1
DAILY SCRUM
Miembro del equipo | Preguntas | Lunes | Martes | Miércoles | Jueves | Viernes | Sábado
Daniel | Qué se hizo ayer? |  | N/A
| Qué se hará hoy? |  | Creacion BD
| Existe algún bloqueo para desarrollar la actividad? |  | N/A
Jerson | Qué se hizo ayer? |  | N/A
| Qué se hará hoy? |  | Asignacion de tareas
| Existe algún bloqueo para desarrollar la actividad? |  | N/A
Monsalve | Qué se hizo ayer? |  | N/A
| Qué se hará hoy? |  | Escoger la plantilla boostrap
| Existe algún bloqueo para desarrollar la actividad? |  | N/A
Santiago | Qué se hizo ayer? |  | N/a
| Qué se hará hoy? |  | Creacion del git
| Existe algún bloqueo para desarrollar la actividad? |  | N/A

## SPRINT 2
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday
Daniel | Qué se hizo ayer? |  | N/A
| Qué se hará hoy? |  | Actividad PB-01
| Existe algún bloqueo para desarrollar la actividad? |  | N/A
Jerson | Qué se hizo ayer? |  | N/A
| Qué se hará hoy? |  | Actividad PB-02
| Existe algún bloqueo para desarrollar la actividad? |  | N/A
Monsalve | Qué se hizo ayer? |  | N/A
| Qué se hará hoy? |  | Actividad PB-03
| Existe algún bloqueo para desarrollar la actividad? |  | N/A
Santiago | Qué se hizo ayer? |  | N/a
| Qué se hará hoy? |  | Actividad PB-04
| Existe algún bloqueo para desarrollar la actividad? |  | N/A

## SPRINT 3
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday
Sebastian | What did you you do yesterday? |  | N/A
| What are doing today? |  | Actividad PB-06
Is there anything blocking you?
Monsalve | What did you you do yesterday? |  | Avance de modulo de aprendices
| What are doing today? |  | Actividad PB-07
Is there anything blocking you?
Jerson | What did you you do yesterday? |  | Modulo de crear usuarios TERMINADO
| What are doing today? |  | Correcion del modulo de crear usuarios por el cambio de la BD
| Is there anything blocking you? |  | Problemas con las credenciales de git
Daniel | What did you you do yesterday? |  | Login TERMINADO
| What are doing today? |  | Actividad PB-09
Is there anything blocking you?
Santiago | What did you you do yesterday? |  | Avance modulo de cursos
| What are doing today? |  | Actividad PB-10
Is there anything blocking you?

## SPRINT 4
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday
Sebastian | What did you you do yesterday? |  | Actividad PB-06
| What are doing today? |  | Continuar con la actividad PB-06
Is there anything blocking you?
Monsalve | What did you you do yesterday? |  | Avance en la Actividad PB-07
| What are doing today? |  | Continuar con la actividad PB-07
Is there anything blocking you?
Jerson | What did you you do yesterday? |  | Correcion del modulo de crear usuarios por el cambio de la BD
| What are doing today? |  | Organización del contenido de la interfaz del usuario (Barra de navegacion
Is there anything blocking you?
Daniel | What did you you do yesterday? |  | Actividad PB-09
| What are doing today? |  | Organizar las consultas fallidas por el cambio de la BD
Is there anything blocking you?
Santiago | What did you you do yesterday? |  | Actividad PB-10
| What are doing today? |  | Continuacion con la actividad PB-10, y comienzo de la PB-11
Is there anything blocking you?